## FLL Project Plan
Task ID | Week | Category | Task Description | Assignee | Status | Notes | Type | Priority | Start date | End date | Due date
FLL-W01-01 | 1 | Project Mgmt & Core Values | Establish roles; set goals; review rubrics |  | Not Started |  | Task
FLL-W01-02 | 1 | Innovation Project | Brainstorm problems; unpack season theme |  | Not Started |  | Task
FLL-W01-03 | 1 | Robot Design | Sort parts; build basic drive bases |  | Not Started |  | Task
FLL-W01-04 | 1 | Robot Game | Build mission models; review rulebook |  | Not Started |  | Task
FLL-W02-05 | 2 | Project Mgmt & Core Values | Create team contract; practice teamwork |  | Not Started |  | Task
FLL-W02-06 | 2 | Innovation Project | Select 1-2 problems; identify experts |  | Not Started |  | Task
FLL-W02-07 | 2 | Robot Design | Test base chassis stability |  | Not Started |  | Task
FLL-W02-08 | 2 | Robot Game | Select initial missions; map routes |  | Not Started |  | Task
FLL-W03-09 | 3 | Project Mgmt & Core Values | Discuss "Inclusion" & "Discovery" |  | Not Started |  | Task
FLL-W03-10 | 3 | Innovation Project | Finalize problem; research existing solutions |  | Not Started |  | Task
FLL-W03-11 | 3 | Robot Design | Start passive/active attachments |  | Not Started |  | Task
FLL-W03-12 | 3 | Robot Game | Write pseudocode; basic navigation |  | Not Started |  | Task
FLL-W04-13 | 4 | Project Mgmt & Core Values | Appoint weekly PM; team-building |  | Not Started |  | Task
FLL-W04-14 | 4 | Innovation Project | Brainstorm solutions; schedule interview |  | Not Started |  | Task
FLL-W04-15 | 4 | Robot Design | Standardize attachment mechanisms |  | Not Started |  | Task
FLL-W04-16 | 4 | Robot Game | Program first 2-3 missions on mat |  | Not Started |  | Task
FLL-W05-17 | 5 | Project Mgmt & Core Values | Review goals; practice Gracious Professionalism |  | Not Started |  | Task
FLL-W05-18 | 5 | Innovation Project | Select final solution; draft design |  | Not Started |  | Task
FLL-W05-19 | 5 | Robot Design | Add sensors (color, gyro) to robot |  | Not Started |  | Task
FLL-W05-20 | 5 | Robot Game | Implement line following/gyro turns |  | Not Started |  | Task
FLL-W06-21 | 6 | Project Mgmt & Core Values | Mid-season check-in; balance workload |  | Not Started |  | Task
FLL-W06-22 | 6 | Innovation Project | Conduct expert interview; gather feedback |  | Not Started |  | Task
FLL-W06-23 | 6 | Robot Design | Refine base robot based on sensors |  | Not Started |  | Task
FLL-W06-24 | 6 | Robot Game | Combine missions into a single run |  | Not Started |  | Task
FLL-W07-25 | 7 | Project Mgmt & Core Values | Discuss "Impact" & "Innovation" |  | Not Started |  | Task
FLL-W07-26 | 7 | Innovation Project | Modify solution based on feedback |  | Not Started |  | Task
FLL-W07-27 | 7 | Robot Design | Finalize attachments; outline presentation |  | Not Started |  | Task
FLL-W07-28 | 7 | Robot Game | Program secondary missions (aim for 5-6) |  | Not Started |  | Task
FLL-W08-29 | 8 | Project Mgmt & Core Values | Start preparing for judging format |  | Not Started |  | Task
FLL-W08-30 | 8 | Innovation Project | Plan 5-min presentation; assign parts |  | Not Started |  | Task
FLL-W08-31 | 8 | Robot Design | Create one-page Executive Summary |  | Not Started |  | Task
FLL-W08-32 | 8 | Robot Game | Run 2.5-min timed matches |  | Not Started |  | Task
FLL-W09-33 | 9 | Project Mgmt & Core Values | Practice Core Values Q&A |  | Not Started |  | Task
FLL-W09-34 | 9 | Innovation Project | Draft & rehearse Project presentation |  | Not Started |  | Task
FLL-W09-35 | 9 | Robot Design | Practice explaining code & design |  | Not Started |  | Task
FLL-W09-36 | 9 | Robot Game | Fix unreliable code; optimize transitions |  | Not Started |  | Task
FLL-W10-37 | 10 | Project Mgmt & Core Values | Share journey (Outreach) |  | Not Started |  | Task
FLL-W10-38 | 10 | Innovation Project | Finalize props; time the presentation |  | Not Started |  | Task
FLL-W10-39 | 10 | Robot Design | Print clean, commented code copies |  | Not Started |  | Task
FLL-W10-40 | 10 | Robot Game | Back-to-back timed runs; finalize order |  | Not Started |  | Task
FLL-W11-41 | 11 | Project Mgmt & Core Values | Full mock judging session |  | Not Started |  | Task
FLL-W11-42 | 11 | Innovation Project | Polish delivery (eye contact, volume) |  | Not Started |  | Task
FLL-W11-43 | 11 | Robot Design | Articulate iteration (what failed/worked) |  | Not Started |  | Task
FLL-W11-44 | 11 | Robot Game | Freeze code; focus on consistency |  | Not Started |  | Task
FLL-W12-45 | 12 | Project Mgmt & Core Values | Pack toolkit; finalize consent forms |  | Not Started |  | Task
FLL-W12-46 | 12 | Innovation Project | Final run-throughs; pack prototype |  | Not Started |  | Task
FLL-W12-47 | 12 | Robot Design | Charge robot; backup code on USB |  | Not Started |  | Task
FLL-W12-48 | 12 | Robot Game | Light practice; celebrate the journey! |  | Not Started |  | Task

## How to use
First Pit — standard FLL task template
This is the starting plan, not a rulebook: delete what your team will not do, and add what it will.
How to use it
1. Fill in Assignee and Status as the season runs. Everything else can stay as it is.
2. Upload it in the app: Tracker → Import from Excel. The preview shows exactly what will be created before anything is saved.
3. Category becomes a work package on your board. The four here map to the four judging areas, so dashboard progress fills in by itself.
4. Week is kept as a label (week-01, week-02 …), so you can group or filter the board by week.
5. Status maps to a board column. Not Started, In Progress, Review and Done are understood; so is any column name your board uses.
6. Assignee is a teammate’s name or the email they sign in with. A name that matches nobody imports unassigned, and the preview says so.
7. Set Type to Subtask to make a row a step of the task above it.
8. Notes becomes the card description.
9. Start date and End date are the planned window; Due date is the deadline. All three are optional and read best as yyyy-mm-dd. The board draws its timeline from the window.
Limits: 200 tasks per upload, 30 subtasks per task, 160 characters per title.
Task list source: FLL_Project_Plan_Task_List.xlsx, supplied by the team 2026-09-17

## Lists (hidden)
Project Mgmt & Core Values | Not Started | Task | Low
Innovation Project | In Progress | Subtask | Medium
Robot Design | Review |  | High
Robot Game | Done |  | Urgent