## Granular Task List
Task ID | Week | Category | Task Description | Assignee | Status | Notes
FTC-CTL-01 | 1 | Control | Initialize season GitHub repository for team code |  | Not Started
FTC-CTL-02 | 1 | Control | Update Control Hub and Driver Hub firmware/apps |  | Not Started
FTC-DES-01 | 1 | Design | Set up team workspace in Onshape and assign roles |  | Not Started
FTC-GEN-01 | 1 | General | Review Game Manual 1 rules and requirements |  | Not Started
FTC-GEN-02 | 1 | General | Review Game Manual 2 game-specific rules |  | Not Started
FTC-GEN-03 | 1 | General | Complete team safety and tool use training |  | Not Started
FTC-SUS-01 | 1 | Sustain | Draft initial season budget (parts, registration, travel) |  | Not Started
FTC-SUS-02 | 1 | Sustain | Create sponsorship pitch deck |  | Not Started
FTC-THI-01 | 1 | Think | Create Engineering Portfolio layout/template |  | Not Started
FTC-THI-02 | 1 | Think | Assign portfolio section owners (Design, Code, Outreach) |  | Not Started
FTC-CNT-01 | 2 | Connect | Identify local STEM/engineering professionals for mentorship |  | Not Started
FTC-CTL-03 | 2 | Control | Configure basic hardware map in Android Studio/OnBot |  | Not Started
FTC-DES-02 | 2 | Design | Draft primary drivetrain CAD in Onshape |  | Not Started
FTC-DES-03 | 2 | Design | Inventory REV/goBILDA hardware, motors, and servos |  | Not Started
FTC-INN-01 | 2 | Innovate | Brainstorm novel scoring/intake mechanisms |  | Not Started
FTC-SUS-03 | 2 | Sustain | Identify and list 5-10 potential local sponsors |  | Not Started
FTC-THI-03 | 2 | Think | Document initial brainstorming and game strategy |  | Not Started
FTC-CNT-02 | 3 | Connect | Draft and send mentor outreach emails |  | Not Started
FTC-CTL-04 | 3 | Control | Write teleop skeleton code and basic drive functions |  | Not Started
FTC-DES-04 | 3 | Design | Assemble physical drive chassis |  | Not Started
FTC-DES-05 | 3 | Design | Mount primary drive motors and wheels |  | Not Started
FTC-INN-02 | 3 | Innovate | Build low-fidelity cardboard/wood prototypes of intake |  | Not Started
FTC-RCH-01 | 3 | Reach | Identify community events for robotics demonstrations |  | Not Started
FTC-THI-04 | 3 | Think | Document math, physics, and gear ratio calculations |  | Not Started
FTC-CTL-05 | 4 | Control | Implement encoder-based drive or odometry navigation |  | Not Started
FTC-DES-06 | 4 | Design | Complete CAD for intake and lifting mechanisms |  | Not Started
FTC-INN-03 | 4 | Innovate | Test compliance materials (e.g., surgical tubing types) |  | Not Started
FTC-RCH-02 | 4 | Reach | Coordinate STEM demo at Wake County Public Libraries |  | Not Started
FTC-SUS-04 | 4 | Sustain | Finalize Tech Titans team branding and order shirts |  | Not Started
FTC-THI-05 | 4 | Think | Record Onshape CAD iterations and design decisions |  | Not Started
FTC-CNT-03 | 5 | Connect | Conduct mid-season design review with a professional mentor |  | Not Started
FTC-CTL-06 | 5 | Control | Integrate AprilTag vision pipeline for autonomous |  | Not Started
FTC-DES-07 | 5 | Design | Prepare custom part files and execute 3D printing |  | Not Started
FTC-INN-04 | 5 | Innovate | Refine custom mechanism based on testing metrics |  | Not Started
FTC-RCH-03 | 5 | Reach | Prepare robot and presentation materials for public interaction |  | Not Started
FTC-SUS-05 | 5 | Sustain | Execute new member recruitment and onboarding plan |  | Not Started
FTC-CNT-04 | 6 | Connect | Host a Q&A session with an industry expert |  | Not Started
FTC-CTL-07 | 6 | Control | Test and tune autonomous pathing and PID loops |  | Not Started
FTC-DES-08 | 6 | Design | Mount scoring mechanisms and complete wire management |  | Not Started
FTC-RCH-04 | 7 | Reach | Present team progress at local school STEM night |  | Not Started
FTC-GEN-04 | 8 | General | Run practice match scrimmages and driver practice |  | Not Started
FTC-GEN-05 | 8 | General | Complete full robot inspection checklist |  | Not Started
FTC-THI-06 | 8 | Think | Finalize Engineering Portfolio for judging sessions |  | Not Started