## FTC Project Plan
Task ID | Week | Category | Task Description | Assignee | Status | Notes | Type | Priority | Start date | End date | Due date
FTC-CTL-01 | 1 | Control | Initialize season GitHub repository for team code |  | Not Started |  | Task
FTC-CTL-02 | 1 | Control | Update Control Hub and Driver Hub firmware/apps |  | Not Started |  | Task
FTC-DES-01 | 1 | Design | Set up team workspace in Onshape and assign roles |  | Not Started |  | Task
FTC-GEN-01 | 1 | General | Review Game Manual 1 rules and requirements |  | Not Started |  | Task
FTC-GEN-02 | 1 | General | Review Game Manual 2 game-specific rules |  | Not Started |  | Task
FTC-GEN-03 | 1 | General | Complete team safety and tool use training |  | Not Started |  | Task
FTC-SUS-01 | 1 | Sustain | Draft initial season budget (parts, registration, travel) |  | Not Started |  | Task
FTC-SUS-02 | 1 | Sustain | Create sponsorship pitch deck |  | Not Started |  | Task
FTC-THI-01 | 1 | Think | Create Engineering Portfolio layout/template |  | Not Started |  | Task
FTC-THI-02 | 1 | Think | Assign portfolio section owners (Design, Code, Outreach) |  | Not Started |  | Task
FTC-CNT-01 | 2 | Connect | Identify local STEM/engineering professionals for mentorship |  | Not Started |  | Task
FTC-CTL-03 | 2 | Control | Configure basic hardware map in Android Studio/OnBot |  | Not Started |  | Task
FTC-DES-02 | 2 | Design | Draft primary drivetrain CAD in Onshape |  | Not Started |  | Task
FTC-DES-03 | 2 | Design | Inventory REV/goBILDA hardware, motors, and servos |  | Not Started |  | Task
FTC-INN-01 | 2 | Innovate | Brainstorm novel scoring/intake mechanisms |  | Not Started |  | Task
FTC-SUS-03 | 2 | Sustain | Identify and list 5-10 potential local sponsors |  | Not Started |  | Task
FTC-THI-03 | 2 | Think | Document initial brainstorming and game strategy |  | Not Started |  | Task
FTC-CNT-02 | 3 | Connect | Draft and send mentor outreach emails |  | Not Started |  | Task
FTC-CTL-04 | 3 | Control | Write teleop skeleton code and basic drive functions |  | Not Started |  | Task
FTC-DES-04 | 3 | Design | Assemble physical drive chassis |  | Not Started |  | Task
FTC-DES-05 | 3 | Design | Mount primary drive motors and wheels |  | Not Started |  | Task
FTC-INN-02 | 3 | Innovate | Build low-fidelity cardboard/wood prototypes of intake |  | Not Started |  | Task
FTC-RCH-01 | 3 | Reach | Identify community events for robotics demonstrations |  | Not Started |  | Task
FTC-THI-04 | 3 | Think | Document math, physics, and gear ratio calculations |  | Not Started |  | Task
FTC-CTL-05 | 4 | Control | Implement encoder-based drive or odometry navigation |  | Not Started |  | Task
FTC-DES-06 | 4 | Design | Complete CAD for intake and lifting mechanisms |  | Not Started |  | Task
FTC-INN-03 | 4 | Innovate | Test compliance materials (e.g., surgical tubing types) |  | Not Started |  | Task
FTC-RCH-02 | 4 | Reach | Coordinate STEM demo at Wake County Public Libraries |  | Not Started |  | Task
FTC-SUS-04 | 4 | Sustain | Finalize Tech Titans team branding and order shirts |  | Not Started |  | Task
FTC-THI-05 | 4 | Think | Record Onshape CAD iterations and design decisions |  | Not Started |  | Task
FTC-CNT-03 | 5 | Connect | Conduct mid-season design review with a professional mentor |  | Not Started |  | Task
FTC-CTL-06 | 5 | Control | Integrate AprilTag vision pipeline for autonomous |  | Not Started |  | Task
FTC-DES-07 | 5 | Design | Prepare custom part files and execute 3D printing |  | Not Started |  | Task
FTC-INN-04 | 5 | Innovate | Refine custom mechanism based on testing metrics |  | Not Started |  | Task
FTC-RCH-03 | 5 | Reach | Prepare robot and presentation materials for public interaction |  | Not Started |  | Task
FTC-SUS-05 | 5 | Sustain | Execute new member recruitment and onboarding plan |  | Not Started |  | Task
FTC-CNT-04 | 6 | Connect | Host a Q&A session with an industry expert |  | Not Started |  | Task
FTC-CTL-07 | 6 | Control | Test and tune autonomous pathing and PID loops |  | Not Started |  | Task
FTC-DES-08 | 6 | Design | Mount scoring mechanisms and complete wire management |  | Not Started |  | Task
FTC-RCH-04 | 7 | Reach | Present team progress at local school STEM night |  | Not Started |  | Task
FTC-GEN-04 | 8 | General | Run practice match scrimmages and driver practice |  | Not Started |  | Task
FTC-GEN-05 | 8 | General | Complete full robot inspection checklist |  | Not Started |  | Task
FTC-THI-06 | 8 | Think | Finalize Engineering Portfolio for judging sessions |  | Not Started |  | Task

## How to use
First Pit — standard FTC task template
This is the starting plan, not a rulebook: delete what your team will not do, and add what it will.
How to use it
1. Fill in Assignee and Status as the season runs. Everything else can stay as it is.
2. Upload it in the app: Tracker → Import from Excel. The preview shows exactly what will be created before anything is saved.
3. Category becomes a work package on your board. Think, Control, Design, Innovate, Connect, Sustain and Reach map to the seven judged awards, so dashboard progress fills in by itself; General counts toward the season only.
4. Week is kept as a label (week-01, week-02 …), so you can group or filter the board by week.
5. Status maps to a board column. Not Started, In Progress, Review and Done are understood; so is any column name your board uses.
6. Assignee is a teammate’s name or the email they sign in with. A name that matches nobody imports unassigned, and the preview says so.
7. Set Type to Subtask to make a row a step of the task above it.
8. Notes becomes the card description.
9. Start date and End date are the planned window; Due date is the deadline. All three are optional and read best as yyyy-mm-dd. The board draws its timeline from the window.
Limits: 200 tasks per upload, 30 subtasks per task, 160 characters per title.
Task list source: FTC_Project_Plan_TaskList.xlsx, supplied by the team 2026-10-23 (docs/ftc/)

## Lists (hidden)
Think | Not Started | Task | Low
Control | In Progress | Subtask | Medium
Design | Review |  | High
Innovate | Done |  | Urgent
Connect
Sustain
Reach
General